|  | Recommendation | Scope of recommendation i.e. local or regional | Action to take | Lead Agency | Key milestones achieved in enacting recommendation | Target Date | Completion Date and Outcome |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | CFT to continue to roll out its two day domestic abuse training module to all appropriate staff. | Local | - Maintain current training delivery. - Ensure all relevant staff are trained. - Undertake review of training outcomes. | CFT | - Completion of training. - Qualitative review of training outcomes reviewed. | 30/06/20 |  |
| 2 | CFT to assist with the development of the adult safeguarding (including domestic abuse) training commissioned by Safer Cornwall Partnership. | Local | - Undertake joint review current adult safeguarding. - Identify areas for joint delivery if appropriate. - Implement Training Strategy. - Deliver Training. - Review outcomes of training. | CFT | - Course content reviewed. - Training Strategy Implemented. - Training delivered. - Outcomes of training reviewed. | 31/05/20 |  |
| 3 | CFT to deliver a learning from experience workshop about this case and share learning and changes to practice. | Local | - Plan and deliver workshop. - Review outcomes of workshop. | CFT | - Workshop planned. - Workshop delivered. - Outcomes of workshop reviewed. | 31/7/20 |  |
| 4 | CFT to implement and disseminate to all staff the new SAB multi agency ‘high risk behaviours policy’ and the ‘self-neglect, rough sleepers and hoarding protocol’. | Local | - Publish protocol and policy. - Implement communications strategy to ensure all relevant staff are aware of policy/protocol. | CFT | - Policy & protocol published. - Details circulated to all frontline staff. | 30/04/20 |  |
| 5 | CFT to develop a self-neglect campaign / strategy to raise awareness in services which includes providing training on self-neglect, testing/assessing capacity and executive capacity / legal perspectives. | Local | - Develop campaign /Strategy. - Develop communications Strategy. - Implement strategy | CFT | - Campaign/Strategy developed. - Communications strategy developed. - Communications strategy implemented. | 31/07/20 |  |
| 6 | CFT to review MDTs, referral meetings and one to one supervision to ensure that adult/children safeguarding is part of these discussions (including appropriate referrals to CFT’s Adult Safeguarding Team) and there is evidence of challenge. | Local | - Review current policy and & practice. - Re-write and implement policy where necessary. - Communicate policy to all staff. - Quality assure operational practice. | CFT | - Policy & practice Reviewed. - Revised policy implemented. - Changes communicated to all relevant staff. | 31/05/20 |  |
| 7 | CFT to audit all cases of adults who use substances to identify numbers where there are concerns about capacity, self-neglect and exploitation to consider whether a review of case is needed under SAB protocols. | Local | - Conduct audit. - Refer relevant cases. - Communicate areas for improvement to all staff. - Quality assure operational practice. | CFT | - Audit conducted. - Relevant cases referred. - Changes implemented as necessary. | 31/06/20 |  |
| 8 | CFT to implement plans for a health based IDVA to be available at Treliske Hospital within the new Service Level Agreement/Contract with Firstlight. | Local | - Implement Service level agreement. - Recruit IDVA. | CFT | - Service level agreement implemented. - IDVA in post. | 30/09/19 |  |
| 9 | Adult Social Care services to undertake a review of all current cases to identify issues impacting on adherence to agreed time scales for the completion of safeguarding meetings. | Local | - Review current cases. - Identify relevant issues. - Implement change where necessary. - Communicate areas for improvement to all staff. - Quality assure operational practice. | Adult Social Care | - Review completed. - Policy & practice reviewed. - Changes implemented. | 31/06/20 |  |
| 10 | Adult Social Care to reinforce the need for comprehensive recording practices to all staff and review current supervision practices to ensure that quality assurance measures are effective within the service. | Local | - Review current supervision practices and identify gaps. - Amend policies/practice. - Deliver Communications Strategy to ensure staff are aware of changes. | Adult Social Care | - Practice reviewed. - Policies amended. - Communications plan delivered. | 30/06/20 |  |
| 11 | Addaction staff to undertake additional training specific to dealing with ‘crack users’. | Local | - Identify relevant training. - All staff to undertake training. - Quality review training. | Addaction | - Training delivered and reviewed. | 31/05/20 |  |
| 12 | Devon and Cornwall police to review and improve the current mobile data technology to ensure frontline officers access to research subjects on their devices and to ensure a timely upload of dash information onto force systems. | Local | - Review existing mobile data technology. - Implement change (where feasible). | Devon and Cornwall Police | - Review completed. - Change implemented. | 30/06/20 |  |
| 13 | GP surgery to review current practice to ensure that domestic abuse is routinely explored with patients. | Local | - Review existing practice. - Review existing DA policy. - Implement changes to practice. - Quality assure changes and practice | GP Surgery | - Review completed. - Change implemented. - Training delivered if required. | 30/04/20 |  |
| 14 | Addaction to review its information sharing processes to ensure that all relevant material is shared in a timely manner with GP’s. | Local | - Review current process. - Implement process change where necessary. - Communicate policy to all staff. - Quality assure operational practice. | Addaction | - Process review completed. - Change implemented. - Communications policy delivered. | 31/05/19 |  |
| 15 | The relevant GP surgery to implement a formal process were risks and concerns are clearly communicated to Addaction in relation to high risk patients. | Local | - Review current process. - Implement process change where necessary. - Communicate policy to all staff. - Quality assure operational practice. | Primary Care | - Process review completed. - Change implemented. - Communications policy delivered. | 31/05/20 |  |
| 16 | Health and Local Authority Commissioners to jointly oversee the implementation of the Dual Diagnosis Strategy, including multi-agency service leads. | Local | - Implement strategy. - Implement process change where necessary. - Communicate policy to all staff. - Quality assure operational practice. | Health & Local Authority | - Strategy Implemented. - Communications strategy delivered. - Practice quality assured. | 31/05/20 |  |
| 17 | Safer Cornwall to review current refuge facilities in the County to identify capacity for victims of domestic abuse who are experiencing addiction or mental illness. | Local | - Review current refuge facilities. - Implement change were necessary. | Safer Cornwall | - Review completed. - Change implemented. - Communications strategy delivered. | 30/06/20 |  |
| 18 | Cornwall Local Authority to ensure that the new SAB multi-agency ‘High Risk Behaviours Policy and the ‘Self-neglect, Rough Sleepers and Hoarding Protocol’ is effectively implemented across all relevant agencies, incorporated into training and circulated to staff. | Local | - Publish protocol and policy. - Implement communications strategy to ensure all relevant staff are aware of policy/protocol. - Quality assure practice. | Cornwall Local Authority | - Policy & protocol published. - Details circulated to all frontline staff. | 30/06/20 |  |
| 19 | All agencies to ensure that current domestic abuse training programmes include relevant input in relation to executive capacity, duress and freewill. | Local | - Review existing training programmes and lesson plans. - Implement change where necessary. - Quality assure operational practice. | All agencies | - Training reviewed. - Lesson plans amended. - Operational practice reviewed. | 30/06/20 |  |
| 20 | Addaction and mental health services to write, publish and implement an escalation process. | Local | - Review existing practice and policies. - Write process and policy. - Publish process - Quality assure operational practice. | Addaction & CMHT | - Process and policy written. - Process and policy published. - Communications policy delivered. - Practice quality assured. | 31/05/20 |  |
| 21 | The current high risk behaviours policy should be amended to ensure that in complex cases a statutory agency should take the lead role in coordinating services. | Local | - Review Policy. - Amend Policy. - Changes communicated to all relevant staff. | Safer Cornwall. | - Policy reviewed. - Policy amended. - Changes communicated to all relevant staff. | 30/04/20 |  |
| 22 | CMHT and Addaction to implement a meeting structure to enable discussions to take place regarding joint care plans. | Local | - Implement meeting structure. - Review meeting structure. | CMHT & Addaction | - Meeting structure implemented. | 30/04/20 |  |